Lincoln Community Larder

Business Plan 2025/26

This plan complements our Strategic Plan 2024/27 and sets out, in a more detailed manner, how we will undertake the operational and practical elements of that plan.  Importantly, it identifies the key tasks and activities, the individuals who have agreed to lead that task and when we hope to complete it.

Moving forwards we will refresh this plan every year.  The Chair will maintain the plan, map progress and report formally to board mid -year and end of year, but any areas that become problematic can be considered at any time.

| Index | Activity | Strategic Plan reference | Lead person | Completion by | Notes | Status (red = in exception, Amber = behind time or some issues, Green = On track Blue = delivered Clear = yet to start |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |
| 2 | Food Sourcing |  |  |  |  |  |  |
| 3 | Seek best value combined with ease of delivery – currently key suppliers being Sainsbury and Bookers | 1 a) | Larder Coordinator | Ongoing |  |  |  |
| 4 | Manage purchase of supplies, tracking budget in collaboration with the Treasurer to ensure cash flow is managed responsibly | 4 A 4 B t) | Larder Coordinator | Ongoing - monthly |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 | Food Storage and Packing |  |  |  |  |  |  |
| 7 | Manage warehouse operation on an ongoing basis coordinating activity to ensure deliveries received and orders prepared. | 1 a) | Warehouse coordinator | Ongoing |  |  |  |
| 8 | Manage physical move to new warehouse across the road |  | Larder coordinator/Chair |  |  |  |  |
| 9 | Manage financial aspects of warehouse relocation – rates, rent, insurances etc |  | Finance sub-group |  |  |  |  |
| 10 | Food Distribution |  |  |  |  |  |  |
| 11 | Maintaining contact with key larder hub managers and partner bodies in relation to operational matters | 3 f) | Larder Coordinator | Regular report to Trustee Board |  |  |  |
| 12 | Monitor demand levels and apprise Trustee Board to enable financial and demand planning | 4 A | Larder Coordinator | Regular report to Trustee Board |  |  |  |
| 13 | Develop additional offer to homeless clients in partnership with Mint Lane Cafe |  | Chair/Larder Coordinator | 1 October 2025 | Hot meal voucher system to be developed and agreed to enable us to give £4.50 vouchers to homeless client for meal at Mint Lane Café, enabling access to further services |  |  |
| 14 | Volunteers |  |  |  |  |  |  |
| 15 | Maintain up to date register of volunteers | 4 B h) l) | Volunteer coordinator | Regular report to Trustee Board |  |  |  |
| 15 | Sustain contacts with volunteer agencies | 4 B l) | Volunteer coordinator | To be agreed |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 | Identify small range of volunteer roles with different job specifications/time demands | 4 B h) l) | Chair/Volunteer coordinator | To be agreed | Aim to maximise usage of volunteers coming forwards and plan to meet our needs for current workloads |  |  |
| 19 | Seek supermarket lead and team for Autumn campaign | 4 A h) | Chair/Volunteer coordinator | To be agreed | Considering supermarket visits to boost customer donations – Probable date Spring 2026 |  |  |
| 20 | Conduct volunteer skills audit/ build database – to enable better succession planning etc |  | Chair | Autumn 2025 |  |  |  |
| 21 | Fundraising |  |  |  |  |  |  |
| 22 | Proactively seek funding opportunities | 4 A f) g) | Finance sub-group (Chair/Treasurer/TT) | ongoing |  |  |  |
| 23 | Building ‘on the shelf’ projects to bid for - being agile | 4 A f) g) | Finance sub-group (Chair/Treasurer/TT) | ongoing |  |  |  |
| 24 | Proactively seek funding opportunities | 4 A f) g) | Finance sub-group (Chair/Treasurer/TT) | ongoing |  |  |  |
| 25 |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |
| 28 | Food Donations |  |  |  |  |  |  |
| 29 | Harvest festival management | 4 A h) | Harvest coordinator | ongoing |  |  |  |
| 30 | Supermarket static point collections | 4 A h) | Larder coordinator | TBA | Need to map current activity - Chair |  |  |
| 31 | Linking in with planned events (Santa run etc) – Chair to contact relevant body | 4 A h) | Chair | November 2025 |  |  |  |
| 32 | Supermarket team visits – develop Autumn campaign | 4 A h) | Chair/Volunteer coordinator/Larder coordinator – seek volunteer leader | November 2024 | On ice whilst warehouse move delivered – revisit after Harvest Festival collections – probable date Spring 2026 |  |  |
| 33 |  |  |  |  |  |  |  |
| 34 |  |  |  |  |  |  |  |
| 35 |  |  |  |  |  |  |  |
| 36 | Communications |  |  |  |  |  |  |
| 37 | Social media and proactive comms - | 4 C G | Communications lead – Wendy Hope | Comms lead to provide regular activity reports to the Trustee Board |  |  |  |
| 38 | Newsletter to volunteers - | 4 B l) 4G 4C | Chair | Three per year – Spring, Autumn, Xmas, plus with any exceptional event | Last news email to all volunteers was at the time of the warehouse move, August 2025 Need to be more regular in year ahead |  |  |
| 39 | Build regular contact with Outreach leaders | 4 B l) 4G | Chair |  | Welton visited by Chair July 2025 Wragby dormant after principal volunteer left. Ermine needs a visit and Martin. St Giles is represented at Board by a trustee. |  |  |
| 40 | Website management – rebuild on new platform/ private members area for docs/minutes etc? | 4C | Chair/Vice Chair | Live by March 2025 | Carried forward for development by Spring 2026 |  |  |
| 41 | IT system for referrals – maintain with ACTs Trust | 5 | Chair/Vice Chair | Ongoing |  |  |  |
| 42 | Relationship management and networking |  |  |  |  |  |  |
| 43 | Represent Larder at Greater Lincolnshire Food Partnership | 4G | Chair | Report activity regularly to Board | Chair now a director of the partnership |  |  |
| 44 | Get tips re available sources of finance/support | 4G | All | Ongoing | Keep our ears open and pass tips to Finance sub-group |  |  |
| 45 | Build better relationship with Coop as partner with strong potential for future | 4G | Chair |  | Chair meets Coop rep at G Lincs Food Partnership – little activity recently |  |  |
| 46 |  |  |  |  |  |  |  |
| 47 |  |  |  |  |  |  |  |
| 48 |  |  |  |  |  |  |  |
| 49 | Financial Management |  |  |  |  |  |  |
| 50 | Manage day to day financial records and bank accounts | 4 B t) | Treasurer | Report activity regularly to Board |  |  |  |
| 51 | Manage Restricted (Investment) Reserve and achieve best returns commensurate with risk appetite set by Board | 4 B t) | Finance sub group | Report activity regularly to Board |  |  |  |
| 52 | Quarterly review of rates being achieved with investment reserve to ensure sensible returns | 4 B t) | Finance sub group | Report activity regularly to Board |  |  |  |
| 53 | Manage financial plan and budget for the year | 4 B t) | Finance sub group | Treasurer to report progress at each Trustee Board | See Appendix A (detailed financial plan) |  |  |
| 54 | Buildings, Estate and Equipment |  |  |  |  |  |  |
| 55 | Leases | 4F | Finance sub group |  | Monitor and manage leases |  |  |
| 56 | Maintain IT equipment and software |  | Chair/Larder coordinator |  | Pretty much up to date |  |  |
| 57 | See also lines 8 and 9 re move to new warehouse site |  |  |  |  |  |  |
| 58 |  |  |  |  |  |  |  |
| 59 |  |  |  |  |  |  |  |
| 60 | Governance |  |  |  |  |  |  |
| 61 | Lead and run meetings | 4B | Chair |  |  |  |  |
| 62 | Maintain efficient and effective records of meetings/actions set and Larder Trustee Board correspondence and notes | 4B | Secretary | Ongoing |  |  |  |
| 63 | Maintain agreed schedule of performance data and provide reports to the Trustee Board – how often and what | 5 | Vice Chair | V-C now preparing regular performance report with data trends highlighted for trustee meetings |  |  |  |
| 64 |  |  |  |  |  |  |  |

APPENDIX A – FINANCIAL PLAN AND BUDGET 2025/26